## Summary
Options Appraisal Summary
5-year view. NPV at the Inputs discount rate. All values are formulas.
Option | NPV (€) | IRR | Payback (years) | Year 0 investment (€) | 5-yr benefits (€) | 5-yr costs (€) | Extra loans / yr
A. Do nothing
B. Quick wins
C. Digital + quick wins
Recommended option (highest NPV)
Recommendation: approve Option B now (fast payback, low risk) and Option C as phase 2, funded from Option B's benefits, if the NPV holds at the sensitivity below.
Sensitivity: NPV (€) by benefit realisation factor
Option | 25% | 50% | 75% | 100%
B. Quick wins
C. Digital + quick wins

## Inputs
Business Case Inputs: SME Loan Origination Redesign
Harbour Bank Ireland (fictional). Blue = input; yellow = key assumption. Source column documents every number.
Input | A. Do nothing | B. Quick wins | C. Digital + quick wins | Source / rationale
GENERAL
Discount rate (annual) | 8% |  |  | Bank hurdle rate for change projects (assumption).
Average funded loan (€) | 91208 |  |  | Process analysis: mean amount of funded applications.
Net margin per year on a funded loan | 1.8% |  |  | After funding cost, expected credit loss and servicing (assumption).
Average loan life (years) | 3 |  |  | SME term loans 1 to 7 years; average outstanding life (assumption).
Benefit realisation factor | 50% |  |  | Only half of the modelled extra loans are counted, for prudence.
Underwriter cost per hour (€) | 55 |  |  | Fully loaded cost (assumption).
Relationship manager cost per hour (€) | 45 |  |  | Fully loaded cost (assumption).
VOLUMES (per year)
Extra funded loans vs today (modelled) | 0 | 455 | 685 | Process analysis notebook, section 5: fewer withdrawals from faster decisions and complete applications.
Credit assessments | 5642 | 5642 | 5642 | Event log, last 12 months.
Document requests (today) | 3883 | 3883 | 3883 | Event log, last 12 months.
EFFICIENCY
Minutes re-keying financials per assessment | 45 | 45 | 45 | Time study with underwriters (workshop estimate).
Reduction in re-keying | 0% | 0% | 80% | C: open banking / accounting-software data feed replaces manual spreading.
Minutes of RM time per document request | 40 | 40 | 40 | RM workshop estimate (call, email, chase, check).
Reduction in document requests | 0% | 50% | 80% | B: digital checklist & upload. C: plus pre-filled data via open banking.
COSTS (€)
One-off cost: year 0 | 0 | 450000 | 1500000 | B: policy change, checklist, portal config, training. C: adds platform build.
One-off cost: year 1 | 0 | 0 | 900000 | C: integration and migration in year 1.
Annual run cost (from year 1) | 0 | 120000 | 380000 | Licences, support, credit forum time.
RAMP-UP of benefits
Year 1 | 0% | 50% | 25% | Share of full benefit achieved.
Year 2 | 0% | 100% | 75%
Year 3 | 0% | 100% | 100%
Year 4 | 0% | 100% | 100%
Year 5 | 0% | 100% | 100%

## Cash_Flows
Five-Year Cash Flows by Option (€)
All cells are formulas on the Inputs sheet.
A. Do nothing | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Revenue benefit: extra loans funded
Efficiency: underwriter re-keying saved
Efficiency: RM document chasing saved
One-off costs
Run costs
Net cash flow
Cumulative cash flow
B. Quick wins | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Revenue benefit: extra loans funded
Efficiency: underwriter re-keying saved
Efficiency: RM document chasing saved
One-off costs
Run costs
Net cash flow
Cumulative cash flow
C. Digital + quick wins | Year 0 | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 | Total
Revenue benefit: extra loans funded
Efficiency: underwriter re-keying saved
Efficiency: RM document chasing saved
One-off costs
Run costs
Net cash flow
Cumulative cash flow